## Tasks
Task ID | Task Name | Task Description | Staff Involved | Task Estimated Time (Hours)
| Research Safari Videos | The purpose is to collect data on how sarfari guides speak and the words they use so we can create our mockomentory for our dog Chewy. | Director
| Create the script | The writter/author will create the script taking into account the intention of this film which is creating a mockomentory revolving our our house and our dog. | Writter
| Create the story board based on the script. | The designer will create sketches presenting the dynamics of how this safari will be told to the users. | Designer/Writter/Author
| Kick off project with the team | Introduce team members so the understand what they are shooting and the dynamics to use to create the film. | All
| Prepare Film Equipment at location | Here all the equipment should be prepared at the first location where the first scene will be recorded. | Camera Man
| Shoot Scene in main area of the home | Here the film creation take places at the different locations. The safari guide and interviewer should follow the director's intructions according to the script defined. | Camera Man, Director, Interviewer, Safari Guide
Shoot Scene in The backyard
Shoot Scene in The Bed room
Shoot Scene in The kitchen
Shoot Scene Near the toy area
Shoot final Scene in the main area of the home
| Post Production Work from Raw Material | At this point, all the story was shooted and now the post production engineer will create the film according to the director's instructions. In this step, the engineer must make the different objects selectable in the film so the user can interact with them. | Post Production Engineer, Director
| Film Wrap Up | At this point, the material is ready to be presented to a marketing team so they can propose the best way to sell this product. | All

## Staff
Role | Description | Estimated Amount of Hour Needed
CAMERA MAN | This person will be responsible for shooting the video following the directions of the director | 12
DIRECTOR | This person will be responsible for defining how the film will be created based on the script.and story board | 120
POST PRODUCTION EDITOR | This person will be responsible for creating the finalized video from the raw material created during the film. | 120
WRITER | This person will be the one creating the story and the script. This person will work together with the director and designer. | 40
DESIGNER | This person is responsible for creating the story board. This person will work together with the writer and director. | 40
SAFARI GUIDE | This person will be responsible of conducting the safari. | 5
PRODUCER | The person/company paying for the expenses that involves creating the material. | 40
| TOTAL | 377 | Hours

## Budget
Type | Item | Unit Price (USD) | Number of Units | Price (USD)
Hardware | Gear 360 | 350 | 1 | 350
Hardware | TRIPOD | 300 | 2 | 600
Hardware | H5 Audio Recorder | 350 | 1 | 350
Software | ADOBE PREMIERE (1 YEAR) | 30 | 1 | 30
Hardware | LAPTOP FOR COMPUTER-RELATED WORK (2) | 2000 | 2 | 4000
Total | TOTALS | 3030 | 7 | 5330